## tasks
Predicted Submission Week: |  |  |  |  | 35
subject | Task | Priority | State | Owner | Week of completion | calendary date
home page | replace pricing with products images and prices | 5 |  | Eliyahu | 12 | 21.3-27.3
| add contact pane\page | 4 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| place holders for adds? | 2 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| add list of registered users? | 2 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| improve UI: change design, colors | 3 |  | Shahar/Eliyahu | 15 | 11.4-17.4
server side | upload images relating to the project and not generic ones | 5 | Done | Shahar | 10 | 7.3-13.3
| change dbURL and driverURL and more parameters from hard coded to parameters in web.xml file | 4 | Done | Shahar | 10 | 7.3-13.3
| add order class | 5 | Perliminary | Eliyahu | 10 | 7.3-13.3
| add product class | 5 | Perliminary | Eliyahu | 10 | 7.3-13.3
| add ordering servlet to handle new orders | 5 |  | Eliyahu | 11 | 14.3-21.1
| add insert, find and update queries for order | 5 |  | Eliyahu | 11 | 14.3-21.1
| add "new order" hadeling to back-end | 5 |  | Eliyahu | 10 | 7.3-13.3
| add 'clicked' field to message class | 5 |  | Shahar | 14 | 4.4-10.4
| add insert, find, update and delete queries for product | 5 |  | Shahar\Eliyahu | 11 | 14.3-21.1
user page | choose and upload images | 5 | Done | Shahar | 10 | 7.3-13.3
| show user name in header | 4 | Done | Shahar | 10 | 7.3-13.3
| show user details and allow edit options | 5 | Done | Shahar | 10 | 7.3-13.3
| show messages threads | 5 |  | Shahar | 12 | 21.3-27.3
| add name to uploaded images | 5 |  | Shahar | 12 | 21.3-27.3
| handle same image name error | 4 | Done | Shahar | 10 | 7.3-13.3
| create list of users in the UI | 5 | Done | Shahar | 10 | 7.3-13.3
| complete functionality for 'cancel' and 'upload' buttons | 5 |  | Shahar | 13 | 28.3-3.4
| update clicked message status in db | 5 | Done | Shahar | 13 | 28.3-3.4
| open 'reply' area below chosen message | 5 | Done | Shahar | 13 | 28.3-3.4
| add list of registered users? | 2 | Done | Shahar | 15 | 28.3-3.4
| add multiple files chosen | 4 |  | Shahar | 13 | 28.3-3.4
documentation | create project UML | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| code documentation | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| project specifications | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| testing specifications | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| add testing specification ATP+ATF | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| add specification form | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| testing results | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| fix installation manual | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
order page | add "empty field" error handeling in registration AND sign in forms | 5 |  | Eliyahu | 12 | 21.3-27.3
| add "new order" form to front-end | 5 |  | Eliyahu | 12 | 21.3-27.3
| user sign in or buy as guest | 5 |  | Eliyahu | 12 | 21.3-27.3
| add buying UI (credit card etc.) with no functionality behind it!! | 5 |  | Eliyahu | 12 | 21.3-27.3

## ATP
Acceptance Test Procedure
tested module | Req. ID | Precedure

## specification
module | #requirement | requirement | derived specifications
user page | 1 | user can sign-up to website | registered user can view past orders
| 1.1 |  | registered user can place new order
| 1.2 |  | registered user can start a new project
| 1.3 |  | registered user can add new step(s) to a project
| 1.4 |  | registered user can send messages(s) to other users
| 1.5 |  | registered user can view all messages from any other users(s)
| 1.6 |  | registered user can add comments to his\hers or other registered users projects
| 1.7 |  | registered user can edit personal details
| 1.8 |  | registered user can view personal details
| 2 | user can sign into website | user is presented with 'log-in' form
| 2.1 |  | upon successful registration user is redirected to 'user' page
| 2.2 |  | registration to website under regular user privileges only
| 3 | user can subscribe to letter notification
| 3.1 | user can purchase without sign-in procedure
| 3.2 | user can purchase safely
| 4 | user can send messages
| 4.1 |  | sent message apear on the reciever end
| 4.2 |  | messages include date, sending party, content
| 4.3 |  | messages may include images
| 4.4 |  | user may attach files to message text
| 5 | user may reply to sent message
| 5.1 |  | replied message apear on receiving party UI
| 5.2 |  | replied message apear on sending party UI
| 5.3 |  | replied message may contain file upload option
| 6 | user cannot hide/delete 'admin' messages
| 7 | only user that sent the message can delete it
| 8 | user can hide message, thus it will not bedisplayed on user UI
| 9 | user can see all hidden messages (as long as not deleted)
| 10 | user can see all sent messages (outgoing)
| 11 | user can see all revieved messages by sending user (incoming)
|  | user can perform actions according to user privliges: | (admin, subscriber, client)
admin can add product
admin can remove product
admin can edit product
admin can add new user
admin can edit user
admin can remove user
user can see past (supplied) and present orders
home page | 4 | web page showcases the company's products portfolio
| 5 | web page showcases the company's main interest and business
| 6 | web page showcases the company's contact avanues
| 7 | web page showcases the company's example uses(project management, information sharing etc..)
| 8 | website provides with administrator prevliges | admin can add product
| 8.1 |  | admin can add user
| 8.2 |  | admin can mark users as 'expert', 'professional', 'amature', 'intern'
| 8.3 |  | admin can remove user
| 8.4 |  | admin can view all orders
| 8.5 |  | admin can add\remove suppliers
code | 9 | code version control must be used
| 10 | build tool must be used
| 11 | code should apply most efficient algorithms
| 12 | deployment to both linux and windows platforms
| 13 | code must employ separations of concerns paradigm
| 14 | back end uses OOP
user page | 1 | user can send messages
| 1.1 |  | sent message apear on the reciever end
| 1.2 |  | messages include date, sending party, content
| 1.3 |  | messages may include images
user may attach files to message text
user can view incoming messages
messages are displayed in different color once clicked
user can hide messages
| 2 | user may reply to sent message
replied message apear on receiving party UI
replied message apear on sending party UI
replied message may contain file upload option
| 3 | user can see past orders
user can place a new order
| 4 | user can view/edit personal details
| 5 | user page display data according to privilege (admin, user, super(?)) | (admin) user can view all sold products
(admin) user can add new products
(admin) user can add/remove new/old users