## Sheet1
Predicted Submission Week: |  |  |  |  | 35
subject | Task | Priority | State | Owner | Week of completion
home page | replace pricing with products images and prices | 5 |  | Eliyahu | 12
| add contact pane\page | 4 |  | Shahar/Eliyahu | 15
| place holders for adds? | 2 |  | Shahar/Eliyahu | 15
| add list of registered users? | 2 |  | Shahar/Eliyahu | 15
| improve UI: change design, colors | 3 |  | Shahar/Eliyahu | 15
server side | upload images relating to the project and not generic ones | 5 | Done | Shahar | 10
| change dbURL and driverURL and more parameters from hard coded to parameters in web.xml file | 4 | Done | Shahar | 10
| add order class | 5 | Perliminary | Eliyahu | 10
| add product class | 5 | Perliminary | Eliyahu | 10
| add ordering servlet to handle new orders | 5 |  | Eliyahu | 11
| add insert, find and update queries for order | 5 |  | Eliyahu | 11
| add "new order" hadeling to back-end | 5 |  | Eliyahu | 10
| add insert, find, update and delete queries for product | 5 |  | Shahar\Eliyahu | 11
user page | choose and upload images | 5 | Done | Shahar | 10
| show user name in header | 4 | Done | Shahar | 10
| show user details and allow edit options | 5 | Done | Shahar | 10
| show messages threads | 5 |  | Shahar | 12
| add name to uploaded images | 5 |  | Shahar | 12
| handle same image name error | 4 | Done | Shahar | 10
| create list of users in the UI | 5 | Done | Shahar | 10
| complete functionality for 'cancel' and 'upload' buttons | 5 |  | Shahar | 13
| update clicked message status in db | 5 |  | Shahar | 13
| open 'reply' area below chosen message | 5 |  | Shahar | 13
| add multiple files chosen | 4 |  | Shahar | 13
documentation | create project UML | 2 |  | Shahar\Eliyahu | 15
| code documentation | 3 |  | Shahar\Eliyahu | 15
| project specifications | 3 |  | Shahar\Eliyahu | 15
| testing specifications | 3 |  | Shahar\Eliyahu | 15
| add testing specification ATP+ATF | 3 |  | Shahar\Eliyahu | 15
| add specification form | 3 |  | Shahar\Eliyahu | 15
| testing results | 2 |  | Shahar\Eliyahu | 15
| fix installation manual | 2 |  | Shahar\Eliyahu | 15
order page | add "empty field" error handeling in registration AND sign in forms | 5 |  | Eliyahu | 12
| add "new order" form to front-end | 5 |  | Eliyahu | 12
| user sign in or buy as guest | 5 |  | Eliyahu | 12
| add buying UI (credit card etc.) with no functionality behind it!! | 5 |  | Eliyahu | 12