## Sheet1
Predicted Submission Week: |  |  |  |  | 35
subject | Task | Priority | State | Owner | Week of completion | calendary date
home page | replace pricing with products images and prices | 5 |  | Eliyahu | 12 | 21.3-27.3
| add contact pane\page | 4 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| place holders for adds? | 2 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| add list of registered users? | 2 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| improve UI: change design, colors | 3 |  | Shahar/Eliyahu | 15 | 11.4-17.4
server side | upload images relating to the project and not generic ones | 5 | Done | Shahar | 10 | 7.3-13.3
| change dbURL and driverURL and more parameters from hard coded to parameters in web.xml file | 4 | Done | Shahar | 10 | 7.3-13.3
| add order class | 5 | Perliminary | Eliyahu | 10 | 7.3-13.3
| add product class | 5 | Perliminary | Eliyahu | 10 | 7.3-13.3
| add ordering servlet to handle new orders | 5 |  | Eliyahu | 11 | 14.3-21.1
| add insert, find and update queries for order | 5 |  | Eliyahu | 11 | 14.3-21.1
| add "new order" hadeling to back-end | 5 |  | Eliyahu | 10 | 7.3-13.3
| add 'clicked' field to message class | 5 |  | Shahar | 14 | 4.4-10.4
| add insert, find, update and delete queries for product | 5 |  | Shahar\Eliyahu | 11 | 14.3-21.1
user page | choose and upload images | 5 | Done | Shahar | 10 | 7.3-13.3
| show user name in header | 4 | Done | Shahar | 10 | 7.3-13.3
| show user details and allow edit options | 5 | Done | Shahar | 10 | 7.3-13.3
| show messages threads | 5 |  | Shahar | 12 | 21.3-27.3
| add name to uploaded images | 5 |  | Shahar | 12 | 21.3-27.3
| handle same image name error | 4 | Done | Shahar | 10 | 7.3-13.3
| create list of users in the UI | 5 | Done | Shahar | 10 | 7.3-13.3
| complete functionality for 'cancel' and 'upload' buttons | 5 |  | Shahar | 13 | 28.3-3.4
| update clicked message status in db | 5 | Done | Shahar | 13 | 28.3-3.4
| open 'reply' area below chosen message | 5 | Done | Shahar | 13 | 28.3-3.4
| add list of registered users? | 2 | Done | Shahar | 15 | 28.3-3.4
| add multiple files chosen | 4 |  | Shahar | 13 | 28.3-3.4
documentation | create project UML | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| code documentation | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| project specifications | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| testing specifications | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| add testing specification ATP+ATF | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| add specification form | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| testing results | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| fix installation manual | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
order page | add "empty field" error handeling in registration AND sign in forms | 5 |  | Eliyahu | 12 | 21.3-27.3
| add "new order" form to front-end | 5 |  | Eliyahu | 12 | 21.3-27.3
| user sign in or buy as guest | 5 |  | Eliyahu | 12 | 21.3-27.3
| add buying UI (credit card etc.) with no functionality behind it!! | 5 |  | Eliyahu | 12 | 21.3-27.3

## ATP
Acceptance Test Procedure
tested module | Req. ID | Precedure

## specification
module | #requirement | requirement | derived specifications
user | 1 | user can sign-up to website | registered user can view past orders
| 1.1 |  | registered user can place new order
| 1.2 |  | registered user can start a new project
| 1.3 |  | registered user can add new step(s) to a project
| 1.4 |  | registered user can send messages(s) to other users
| 1.5 |  | registered user can view all messages from any other users(s)
| 1.6 |  | registered user can add comments to his\hers or other registered users projects
| 1.7 |  | registered user can edit personal details
| 1.8 |  | registered user can view personal details
| 2 | user can sign into website | user is presented with 'log-in' form
| 2.1 |  | upon successful registration user is redirected to 'user' page
| 2.2 |  | registration to website under regular user privileges only
| 3 | user can subscribe to letter notification
| 3.1 | user can purchase without sign-in procedure
| 3.2 | user can purchase safely
home page | 4 | web page showcases the company's products portfolio
| 5 | web page showcases the company's main interest and business
| 6 | web page showcases the company's contact avanues
| 7 | web page showcases the company's example uses(project management, information sharing etc..)
| 8 | website provides with administrator prevliges | admin can add product
| 8.1 |  | admin can add user
| 8.2 |  | admin can mark users as 'expert', 'professional', 'amature', 'intern'
| 8.3 |  | admin can remove user
| 8.4 |  | admin can view all orders
| 8.5 |  | admin can add\remove suppliers
code | 9 | code version control must be used
| 10 | build tool must be used
| 11 | code should apply most efficient algorithms
| 12 | deployment to both linux and windows platforms
| 13 | code must employ separations of concerns paradigm
| 14 | back end uses OOP