## tasks
Predicted Submission Week: |  |  |  |  | 35
subject | Task | Priority | State | Owner | Week of completion | calendary date
home page | replace pricing with products images and prices | 5 |  | Eliyahu | 12 | 21.3-27.3
| add contact pane\page | 4 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| place holders for adds? | 2 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| add list of registered users? | 2 |  | Shahar/Eliyahu | 15 | 11.4-17.4
| improve UI: change design, colors | 3 |  | Shahar/Eliyahu | 15 | 11.4-17.4
server side | upload images relating to the project and not generic ones | 5 | Done | Shahar | 10 | 7.3-13.3
| change dbURL and driverURL and more parameters from hard coded to parameters in web.xml file | 4 | Done | Shahar | 10 | 7.3-13.3
| add order class | 5 | Perliminary | Eliyahu | 10 | 7.3-13.3
| add product class | 5 | Perliminary | Eliyahu | 10 | 7.3-13.3
| add ordering servlet to handle new orders | 5 |  | Eliyahu | 11 | 14.3-21.1
| add insert, find and update queries for order | 5 |  | Eliyahu | 11 | 14.3-21.1
| add "new order" hadeling to back-end | 5 |  | Eliyahu | 10 | 7.3-13.3
| add 'clicked' field to message class | 5 |  | Shahar | 14 | 4.4-10.4
| add insert, find, update and delete queries for product | 5 |  | Shahar\Eliyahu | 11 | 14.3-21.1
user page | choose and upload images | 5 | Done | Shahar | 10 | 7.3-13.3
| show user name in header | 4 | Done | Shahar | 10 | 7.3-13.3
| show user details and allow edit options | 5 | Done | Shahar | 10 | 7.3-13.3
| show messages threads | 5 |  | Shahar | 12 | 21.3-27.3
| add name to uploaded images | 5 |  | Shahar | 12 | 21.3-27.3
| handle same image name error | 4 | Done | Shahar | 10 | 7.3-13.3
| create list of users in the UI | 5 | Done | Shahar | 10 | 7.3-13.3
| complete functionality for 'cancel' and 'upload' buttons | 5 |  | Shahar | 13 | 28.3-3.4
| update clicked message status in db | 5 | Done | Shahar | 13 | 28.3-3.4
| open 'reply' area below chosen message | 5 | Done | Shahar | 13 | 28.3-3.4
| add list of registered users? | 2 | Done | Shahar | 15 | 28.3-3.4
| add multiple files chosen | 4 |  | Shahar | 13 | 28.3-3.4
documentation | create project UML | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| code documentation | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| project specifications | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| testing specifications | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| add testing specification ATP+ATF | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| add specification form | 3 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| testing results | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
| fix installation manual | 2 |  | Shahar\Eliyahu | 15 | 11.4-17.4
order page | add "empty field" error handeling in registration AND sign in forms | 5 |  | Eliyahu | 12 | 21.3-27.3
| add "new order" form to front-end | 5 |  | Eliyahu | 12 | 21.3-27.3
| user sign in or buy as guest | 5 |  | Eliyahu | 12 | 21.3-27.3
| add buying UI (credit card etc.) with no functionality behind it!! | 5 |  | Eliyahu | 12 | 21.3-27.3

## ATP
Acceptance Test Procedure
tested module | Req. ID | Precedure

## test User page
requirement | pre condition | instruction | expected result
user can sign-up to website |  | 1. log on to final_project and press 'sign in' | 1. website shows on browser
|  | 2. fill user name and user password | 2. user name and user password are shown
|  | 3. hit enter | 3. browser redirect to 'user-page', and user name is displayed in the upper right corner
user can sign into website |  | 1. log on to final_project and press 'register (sign up)' | 1. website shows on browser
|  | 2. fill user name nickname and user password | 2. user name and user password are shown
|  | 3. hit enter | 3. browser redirect to 'user-page', and user name is displayed in the upper right corner
user can subscribe to letter notification |  | 1. log on to final_project and press subscribe' | 1. website shows on browser
|  | 2. fill user name and email address | 2. user name and email are shown
|  | 3. hit enter | 3. browser stays on 'home-page', and message have been sent to user
user can purchase without sign-in procedure |  | 1. log on to final_project and press 'new order' | 1. website shows on browser
|  | 2. fill ALL (*) marked fields | 2. user name and email are shown
|  | 3. hit enter | 3. browser stays on 'home-page', and message have been sent to user
user can purchase safely |  | open web.xml and search for 'security protocol' | security protocol' has non empty string
user can send messages |  | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'messages' and hit 'more' | 2. menu opens with few options
|  | 3. choose 'new' | 3. an upload file area and text area shows on page with 'send' 'cancel' buttons
|  | 4. choose an image of .png format and write 'this text' text, press 'send' | 4. the message is shown on the user messages area, and the upload area disappears
|  | 5. choose an image of .png format and write 'this text' text, press 'send' | 5. the message is shown on the user messages area, and the upload area disappears
user may reply to sent message | user has at least 1 incoming message | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'messages' | 2. at least 1 incoming message exist
|  | 3. choose 'reply' | 3. an upload file area and text area shows on page with 'send' 'cancel' buttons
|  | 4. choose an image of .png format and write 'this text' text, press 'send' | 4. the message is shown on the user messages area, and the upload area disappears
|  | 5. choose an image of .png format and write 'this text' text, press 'send' | 5. the message is shown on the user messages area, and the upload area disappears
user cannot hide/delete 'admin' messages | registered user | 1. navigate to 'messages' | 1. a 'welcome' message from admin exist WITHOUT 'reply' option
only user that sent the message can delete it |  | TBD | TBD
user can hide message, thus it will not bedisplayed on user UI |  | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'messages' | 2. at least 1 incoming message exist NOT from 'admin'
|  | 3. choose 'hide' | 3. message disappears from 'messages' area
|  | 4. hit ctrl + F5 key | 4. the chosen messages remains unseen
user can see all hidden messages (as long as not deleted) |  | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'messages' | 2. at least 1 incoming message exist NOT from 'admin'
|  | 3. choose 'hide' from message body options | 3. message disappears from 'messages' area
|  | 4. hit ctrl + F5 key | 4. all messages remains
|  | 5. from the 'more' drop down menu choose 'show all messages' | 5. hiden messages reappear
|  | 6. hit ctrl + F5 key | 6. messages remain
user can see all sent messages (outgoing) | at least 1 message sent by user exist | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'messages' | 2. at least 1 outgoing message exist from user
|  | 3. choose 'show sent messages' from drop down menu | 3. only messages sent from sign in user present
|  | 4. hit ctrl + F5 key | 4. all messages remains
user can see all revieved messages according to sending user (incoming) | at least 2 message sent by 2 other users exists | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'messages' | 2. at least 2 coming messages exist from 2 different users
|  | 3. click on the name of the sending user, in the message body | 3. only messages sent from selected user appears
|  | 4. hit ctrl + F5 key | 4. all messages remains
|  | 3. click on the OTHER name of the sending user, in the message body | 5. only messages sent from selected user appears
user can see past (supplied) and present orders | at least 1 order exists | 1. sign in to website with user and password | 1. user page shows 'you are connected as' at the top with user name
|  | 2. navigate to 'orders' | 2. at least 1 order exists with: order number, products and quantity, supplied
user can place new order(s) |  | TBD | TBD
user can perform actions according to user privliges: